## GTM Tasks
Phase | ID | Task | Who | Type | Weeks | Budget | Status
0 — Close in-flight | 0.1 | Time-intel rollups read persisted snapshots (lift 5000 live-scan cap) | Agent | Product | 1-2 |  | Open
0 — Close in-flight | 0.2 | Inbound ServiceNow state-sync (full human-phase timing: ack/mitigate/resolve) | Agent | Product | 1-2 |  | Open
0 — Close in-flight | 0.3 | #85 four per-hop backend metrics + #77 topology polish (health join, canvas on /api/topology/graph, capacity util-binding fix) | Agent | Product | 1-2 |  | Open
0 — Close in-flight | 0.4 | Iris AI P4 remainder; owner applies strict ClickHouse tenant policies | Both | Product | 1-2 |  | Open
0 — Close in-flight | 0.5 | Path Trace STAMP hop metrics: owner answers 4 held design questions, then land held code | Owner then Agent | Product | 1-2 |  | Open
0 — Close in-flight | 0.6 | Brand: pick eye-logo P1-P6, finalize assets (favicon, login, reports, site) | Owner then Agent | Brand | 1-2 |  | Open
0 — Close in-flight | 0.7 | Lab hygiene: lan-sw1 console recovery; confirm NetFlow no longer dry (48h) | Owner | Lab | 1-2 |  | Open
1 — Cloud + cross-seam correlation | 1.1 | #70 Build AWS lab network (VPCs, TGW, VPN to clab lab, EC2 workloads); agent supplies step-by-step runbook | Owner | Lab | 2-6 | $150-300/mo | Open
1 — Cloud + cross-seam correlation | 1.2 | #68 Cloud ingestion, 3-tier causal model: VPC flow logs, CloudWatch health/metrics, CloudTrail change events | Agent | Product | 2-6 |  | Open
1 — Cloud + cross-seam correlation | 1.3 | #81 cloud light-ups: App-Map traffic edges, real health, change timeline, Dependencies tab, source-IP + ENI resolution, app names at all read paths | Agent | Product | 2-6 |  | Open
1 — Cloud + cross-seam correlation | 1.4 | Cloud/DX RCA mislabel fix + seam-graph (unblocked by real AWS) | Agent | Product | 2-6 |  | Open
1 — Cloud + cross-seam correlation | 1.5 | #69 P2 service catalog + svc_flow_rollup + baselines | Agent | Product | 2-6 |  | Open
1 — Cloud + cross-seam correlation | 1.6 | TEST - Cloud E2E: flow logs tenant-scoped in ClickHouse; App-Map edges/health/change RENDERED on real cloud data | Both | Testing | 2-6 |  | Open
1 — Cloud + cross-seam correlation | 1.7 | TEST - Cross-seam correlation: inject faults (drop VPN, blackhole route, sever TGW, kill EC2 app) -> RCA names correct seam + auto-ticket | Both | Testing | 2-6 |  | Open
2 — RCA Accuracy Bench | 2.1 | Build fault-injection scenario suite (extend FortiGate methodology): 30-50 scenarios across link/optical/BGP/OSPF/HW/config/cloud/app | Both | Testing | 5-10 |  | Open
2 — RCA Accuracy Bench | 2.2 | Run full suite repeatedly on lab + AWS; accumulate real incident history | Both | Testing | 5-10 |  | Open
2 — RCA Accuracy Bench | 2.3 | #67 P4 replay calibration; tune 57 enabled signatures; unblock 42 Layer-2-kind backlog templates | Agent | Product | 5-10 |  | Open
2 — RCA Accuracy Bench | 2.4 | TEST - Publish Accuracy Bench Report: precision/recall per class, median time-to-identify, corroboration rate, FP rate + methodology appendix | Both | Testing | 5-10 |  | Open
3 — Scale, HA & reliability | 3.1 | Multi-node Kafka support (clustered profile + docs) | Agent | Product | 8-14 |  | Open
3 — Scale, HA & reliability | 3.2 | K8s/Helm packaging (Phase 2 of #97) | Agent | Product | 8-14 |  | Open
3 — Scale, HA & reliability | 3.3 | Disk/retention guardrails: OpenSearch ILM + watermark alerts, CH/VM retention, self-protection | Agent | Product | 8-14 |  | Open
3 — Scale, HA & reliability | 3.4 | TEST - Load: 5,000 sim devices + 50k flows/s (tgen + SNMP sim), 72h sustained; publish ingest lag + query latency numbers | Both | Testing | 8-14 |  | Open
3 — Scale, HA & reliability | 3.5 | TEST - Chaos/HA: kill each of ~19 services -> no data loss, no silent blind window, watchdog + in-app alerts fire | Both | Testing | 8-14 |  | Open
3 — Scale, HA & reliability | 3.6 | TEST - 30-day soak on VM .123 bundle: memory/disk growth, cert expiry, log rotation | Owner | Testing | 8-14 |  | Open
3 — Scale, HA & reliability | 3.7 | TEST - Backup/restore/DR: runbook + full restore drill onto clean host | Both | Testing | 8-14 |  | Open
3 — Scale, HA & reliability | 3.8 | Stream 6 SaaS-hardening pass: #16 remaining 3 sub-items, #33 users repo, #75, ingest one-way-door decision | Agent | Product | 8-14 |  | Open
4 — Productization & packaging | 4.1 | Build licensing: Ed25519 offline license files, FREE tier default, entitlements, 30-day eval auto-mint (~2 days, design agreed) | Agent | Product | 10-16 |  | Open
4 — Productization & packaging | 4.2 | TEST - Licensing enforcement: free-tier lockouts, expiry, tamper rejection, eval mint, upgrade-in-place | Both | Testing | 10-16 |  | Open
4 — Productization & packaging | 4.3 | BYO / on-prem LLM for Iris AI: Ollama/vLLM/Bedrock/Azure endpoints behind copilot proxy | Agent | Product | 10-16 |  | Open
4 — Productization & packaging | 4.4 | TEST - AI red-team: prompt injection, cross-tenant leakage, output handling, cost/token caps | Both | Testing | 10-16 |  | Open
4 — Productization & packaging | 4.5 | Release engineering: semver, changelog, GPG-signed bundles, versioned upgrade path | Both | Product | 10-16 |  | Open
4 — Productization & packaging | 4.6 | TEST - Upgrade: bundle vN -> vN+1 on live data, zero loss, documented | Both | Testing | 10-16 |  | Open
4 — Productization & packaging | 4.7 | TEST - Fresh-install matrix: Ubuntu 22/24, RHEL 9, fully air-gapped; preflight + CI stay green | Both | Testing | 10-16 |  | Open
4 — Productization & packaging | 4.8 | Evaluator docs site: install, quick-start, admin guide, API reference, integration guides | Agent | Product | 10-16 |  | Open
4 — Productization & packaging | 4.9 | UI final QA: #71 panel-fix sweep, admin wizardization #20, cross-browser, accessibility scan, empty-state audit | Agent | Product | 10-16 |  | Open
5 — Trust & security artifacts | 5.1 | SBOM publication + security-disclosure/CVE process page | Agent | Security | 12-18 |  | Open
5 — Trust & security artifacts | 5.2 | TEST - Re-run IAM/tenancy audit suite + gitleaks/trivy/govulncheck; fix all findings | Agent | Testing | 12-18 |  | Open
5 — Trust & security artifacts | 5.3 | TEST - Third-party penetration test (book early: 4-6 wk lead) | Owner | Testing | 12-18 | $8-25k | Open
5 — Trust & security artifacts | 5.4 | Security whitepaper: zero-trust arch, FORCE-RLS tenancy, vault+TPM, OWASP-LLM, offline build | Agent | Security | 12-18 |  | Open
5 — Trust & security artifacts | 5.5 | SOC 2 Type I kickoff (after incorporation); announce roadmap before completion | Owner | Security | 12-18 | $15-40k | Open
6 — Company formation | 6.1 | Trademark + name clearance for Correlix (USPTO Class 9/42, domains, intl check) - DO FIRST | Owner | Company | 8+ | $1-2k | Open
6 — Company formation | 6.2 | Incorporate: LLC (bootstrap) or Delaware C-Corp (venture) via Stripe Atlas/Clerky; EIN, bank, bookkeeping | Owner | Company | 8+ | ~$500 | Open
6 — Company formation | 6.3 | IP assignment: formally assign all pre-incorporation code/brand to the company | Owner | Company | 8+ |  | Open
6 — Company formation | 6.4 | Founder hygiene: cap table, 83(b) within 30 days if C-Corp, E&O + cyber insurance | Owner | Company | 8+ | $2-4k/yr | Open
6 — Company formation | 6.5 | Legal doc set: EULA/license agreement, privacy policy, ToS, DPA template, support SLA | Owner | Company | 8+ | $2-5k | Open
6 — Company formation | 6.6 | Pricing & packaging sheet: Free / Pro / Enterprise mapped to license entitlements; flat self-hosted tiers | Both | Company | 8+ |  | Open
6 — Company formation | 6.7 | Support model: intake (email + forum/Discord), SLA tiers, install-support runbooks | Both | Company | 8+ |  | Open
7 — Marketing & content | 7.1 | Website on correlix.com: hero positioning, product, accuracy-bench page, security/trust, pricing, docs, free-tier CTA | Both | Marketing | 12-20 |  | Open
7 — Marketing & content | 7.2 | LinkedIn: company page + founder profile; 2-3 posts/wk build-in-public (bench results, RCA war stories, lab screenshots) | Owner | Marketing | 12-20 |  | Open
7 — Marketing & content | 7.3 | Hosted demo environment (tgen-driven live data + guided tour) + 3-5 min demo video | Both | Marketing | 12-20 |  | Open
7 — Marketing & content | 7.4 | Sales collateral: battlecards (ThousandEyes/Datadog/Kentik/Selector/Auvik), ROI one-pager, bench PDF, security whitepaper | Agent | Marketing | 12-20 |  | Open
7 — Marketing & content | 7.5 | Community seeding: r/networking, r/sysadmin, NANOG list, Packet Pushers / podcasts, conference lightning talks | Owner | Marketing | 12-20 |  | Open
7 — Marketing & content | 7.6 | Email capture + newsletter; accuracy bench report as lead magnet | Both | Marketing | 12-20 |  | Open
8 — Design partners & validation | 8.1 | Real-hardware bench: used enterprise gear (Cat9k/Nexus, PA, F5, APs) | Owner | Lab | 14-24 | $3-8k | Open
8 — Design partners & validation | 8.2 | Vendor profiles PA/F5/APs on real gear; Port Intelligence first real-optics render | Agent | Product | 14-24 |  | Open
8 — Design partners & validation | 8.3 | Recruit 3-5 design partners (free enterprise license for feedback + quirks + logo/testimonial rights) | Owner | GTM | 14-24 |  | Open
8 — Design partners & validation | 8.4 | Onboard partners, weekly feedback loop, fix quirks fast, extract 1-2 written case studies | Both | GTM | 14-24 |  | Open
8 — Design partners & validation | 8.5 | NMS integration real-vendor contact validation | Owner | Product | 14-24 |  | Open
8 — Design partners & validation | 8.6 | TEST - Time-to-value: a stranger network engineer installs from docs alone in <1 hour (watch, don't help) | Owner | Testing | 14-24 |  | Open
9 — Launch | 9.1 | Launch-readiness checklist: site live, free tier downloadable, docs public, demo video, bench report, security page, pricing, support intake, signed bundles | Both | GTM | ~24 |  | Open
9 — Launch | 9.2 | Launch motions (same week): Show HN, LinkedIn announcement + testimonials, r/networking, NANOG lightning talk, Product Hunt | Owner | Marketing | ~24 |  | Open
9 — Launch | 9.3 | Post-launch loop: opt-in install telemetry, download->install->license funnel metrics, weekly releases, public roadmap | Both | GTM | 24+ |  | Open

## Testing Checklist
Task ID | Test | Phase | Status
1.6 | Cloud ingestion E2E (rendered on real data) | 1 | Open
1.7 | Cross-seam fault correlation (on-prem <-> cloud) | 1 | Open
2.1-2.2 | Fault-injection suite, 30-50 scenarios | 2 | Open
2.4 | RCA accuracy bench (precision/recall/MTTI) - PUBLISHED | 2 | Open
3.4 | Load: 5k devices / 50k flows/s / 72h - PUBLISHED | 3 | Open
3.5 | Chaos/HA: every service killed, no blind window | 3 | Open
3.6 | 30-day soak on VM bundle | 3 | Open
3.7 | Backup/restore/DR drill | 3 | Open
4.2 | Licensing enforcement | 4 | Open
4.4 | AI red-team (injection/leakage/caps) | 4 | Open
4.6 | Upgrade vN -> vN+1 with live data | 4 | Open
4.7 | Fresh-install matrix (Ubuntu/RHEL/air-gapped) | 4 | Open
5.2 | Tenancy/IAM audit re-run + scanner pass | 5 | Open
5.3 | Third-party penetration test | 5 | Open
8.2 | Real-hardware vendor matrix (incl. real optics) | 8 | Open
8.6 | Stranger time-to-value < 1 hour | 8 | Open
0.2/1.7 | RCA -> ticket E2E vs real ServiceNow PDI | 0/1 | Mock-validated; real PDI open

## Budget
Item | Cost | Phase | Notes
AWS lab network | $150-300 / month | Phase 1 | TGW attachments + VPN + EC2 + flow-log S3
Third-party penetration test | $8,000 - 25,000 | Phase 5 | 4-6 week lead time; book early
SOC 2 Type I | $15,000 - 40,000 | Phase 5 | Auditor + Vanta/Drata; 2-3 months; can trail launch
Used hardware bench | $3,000 - 8,000 | Phase 8 | Cat9k/Nexus, PA, F5, APs
Incorporation + legal docs | $3,000 - 6,000 | Phase 6 | Atlas/Clerky + lawyer review of EULA/ToS/DPA
Business insurance (E&O + cyber) | $2,000 - 4,000 / yr | Phase 6 | Enterprise buyers ask for certificates
Trademark | $1,000 - 2,000 | Phase 6 | USPTO Class 9/42 + counsel
TOTAL cash to GTM (ex-time) | ~$35,000 - 85,000 |  | Most deferrable if bootstrapping (SOC 2 / pen test can trail a quarter)

## Read Me
Correlix - Road to GTM (task workbook)
Generated 2026-07-06 from docs/GTM_PLAN.md (commit 5000f0f). GTM_PLAN.md stays the source of truth; regenerate this sheet when it changes.
Positioning: 'The RCA engine for networks that can't leave the building' - on-prem / air-gapped / sovereign / MSP beachhead.
Critical path: Phase 0 -> 1 (cloud + cross-seam tests) -> 2 (accuracy bench) -> 3 (scale/HA) -> 9 (launch, ~week 24).
Phases 4-8 run in parallel and do not block the critical path. Start Phase 6 (company formation) by week 8 - long lead times.
Who: Owner = you; Agent = Claude-built software; Both = joint (typically owner drives lab/business, agent drives code/harness).
Update the Status column as work lands: Open -> In progress -> Done.